## Overview
Feynman Grand Prize - NDI Systems-Engineering Decomposition & Verification Contract
v0.2 (rules-grounded; TBR-2/3/4/5 resolved) ¦ Public Feynman-Path V&V (open science)
Spine | Hybrid traceability: literal 1995 prize spec as requirements root, mapped to NDI off-board electrically-controlled route (Track 1 spine; Tracks 2-3 dependencies); divergences flagged as contract deviations.
Leaf rule | Each leaf = exactly one experiment OR one simulation/proof with one acceptance criterion.
Prize | $250,000 ¦ announced 1995 ¦ unclaimed ¦ James R. Von Ehr II (Zyvex) & Marc E. Arnold; Foresight Institute
Device 1 | Robotic nanomanipulator: fits entirely in a <=100 nm cube; moves to a directed sequence of positions anywhere within a 50 nm cube; positioning accuracy <=0.1 nm; >=1000 accurate nm-scale positioning motions per second for >=60 consecutive seconds; actions directed by input signals.
Device 2 | 8-bit binary adder: fits entirely in a <=50 nm cube; adds any pair of 8-bit numbers discarding overflow (8-bit output); accepts input signals; output rendered as raised nm-scale bumps on an atomically precise and level surface. (Conventional 8-bit adder ~94 AND/OR/NOT gates; ~37 with XOR - J.S. Hall.)
Submission | >=32 copies of EACH device for analysis and DESTRUCTIVE testing by judges (mass-production demonstration). Self-replication is NOT required to qualify.
Inputs allowed | acoustic, electrical, optical, diffusive-chemical, or mechanical; any MECHANICAL driving input limited to a single linkage that slides or rotates on a single axis (so off-board electrical/optical/chemical drive is explicitly admissible).
Underdefined (gaps) | Well-specified: 100/50 nm geometry, 0.1 nm accuracy, >=1000 motions/s x>=60 s, bump-topography output, 5 input modalities, 32-copy destructive testing. UNDERDEFINED (hypothesis confirmed): operating environment/temperature; exact input-signal encoding; judging/verification methodology beyond destructive testing; time-to-claim window.
Generation map | Prize-grade arm (0.1 nm accuracy, >=1000 moves/s x60 s) = NDI Gen-3+ unless stiffening modeling (A8.2/A1.4) closes the thermal-noise gap; Gen-1 (sub-3 nm closed-loop actuator) is the precursor tier. The adder is a positionally-assembled atomically-precise device (output = topographic bumps) built by arm-class capability + Track-2 mechanosynthesis, not an off-board CPU.
[ownership/IP-chain note redacted for public release] | [ownership/IP-chain note redacted for public release]
Verbatim rules | Foresight Feynman Grand Prize rules (1995), reproduced in Freitas & Merkle, KSRM 4.9.4: The robotic nanomanipulator must fit entirely inside a 100-nm cube, carry out actions directed by input signals of specified types, be able to move to a directed sequence of positions anywhere within a 50-nm cube, complete all directed actions with a positioning accuracy of 0.1 nanometer or better, and perform at least 1,000 accurate, nanometer-scale positioning motions per second for at least 60 consecutive seconds. The adder must fit entirely within a 50-nm cube, and must be capable of adding accurately any pair of 8-bit binary numbers, discarding overflow, accepting input signals of specified types, and producing its output as a pattern of raised nanometer-scale bumps on an atomically precise and level surface. (J.S. Hall: ~94 AND/OR/NOT gates; ~37 with XOR.) Both devices may accept inputs from acoustic, electrical, optical, diffusive chemical, or mechanical means, although any mechanical driving mechanism used for input must be limited to a single linkage that either slides or rotates on a single axis. At least 32 copies of each device must be provided for analysis and destructive testing by judges. The device does not need to demonstrate self-replication to qualify.
Empirical tripwire | EMPIRICAL-VALIDATION flag is MANDATORY at any TRL 3->4 crossing and for every claim about yield, force, signal-to-noise ratio (SNR), or positional/angular accuracy, regardless of TRL.
Verification taxonomy
P | Formal / analytical proof
Machine check: An automated checker returns PASS/FAIL: SAT/SMT/BDD equivalence, symbolic algebra, screw-theory rank test, closed-form inequality evaluator, packing/geometry checker.
Sufficiency: Sufficient alone only for mathematical/logical obligations; physical realism still requires S or E downstream.
S | Computational simulation >= threshold
Machine check: A CI-style sim harness runs the model (DFT/QM, MD/coarse-grained, FEM, PNP/Poisson-Boltzmann, device/SPICE-like, control sim, ML eval) and asserts a quantitative metric against a numeric threshold with stated uncertainty.
Sufficiency: Greens a node only below the empirical tripwire; above it, S de-risks but does not discharge.
E | Empirical acceptance test
Machine check: Instrument output is parsed to a standard schema (Allotrope ASM / structured JSON) and an automated assertion compares the measured value to the spec; PASS/FAIL is reproducible from raw data.
Sufficiency: Required to discharge any node above the empirical tripwire.
Leaf summary (live formulas -> 'VnV Matrix')
Metric | Count
Total leaves
Proof (P)
Simulation (S)
Empirical (E)
Empirical-validation flags

## VnV Matrix
ID | Title | Seg | Parent | Kind | V | Verification tool / method | Machine-checkable check (PASS/FAIL) | Acceptance criterion | Empirical? | Empirical reason | TRL now | TRL tgt | Depends on | Div | Open | Risk | EpiGraph claims
A1.1 | Derive required effective stiffness vs thermal-noise positioning bound | A | A1 | leaf | P | Closed-form k >= kBT/sigma^2 (equipartition) + numeric evaluator | Inequality evaluator recomputes k for each sigma target; asserts table values. | Bound table: sigma=3 nm -> k>=~0.46 pN/nm; sigma=0.1 nm (prize) -> k>=~414 pN/nm; sigma=0.03 nm -> k>=~4.6 N/m (kBT=4.14 pN.nm @300K). | no |  | 4 | 4 |  |  |  | Static bound only; bond-formation dwell variance handled in A1.4.
A1.2 | Simulate as-designed lever positional variance at 300 K | A | A1 | leaf | S | Coarse-grained/MD (oxDNA/Martini) ensemble | Sim harness asserts sigma_RMS over >=5 seeds with CI. | Simulated sigma_RMS <= 3.0 nm for nominal Gen-1 lever; 95% CI reported. | no |  | 3 | 4 | A1.1 |  |  | Force-field accuracy for DNA-on-polymer.
A1.3 | Measure as-built positional/angular dispersion (cross-validated) | A | A1 | leaf | E | cryo-EM class averaging + smFRET dye-geometry assay | ASM/JSON acceptance test asserts measured sigma <= spec; two methods agree. | Measured sigma <= 3 nm (Gen-1 precursor); prize grade is 0.1 nm (Gen-3+); cryo-EM vs smFRET agree within band. | YES | positional/angular accuracy; TRL3->4 | 3 | 4 | A1.2 |  |  | DNA softness may exceed bound -> triggers A1.4/stiffening. | b106a87a-4a3d-45d7-84cc-01faef30c11a
A1.4 | Feedback-cooling / dwell-averaging analysis to reach sub-nm effective placement | A | A1 | leaf | P | Control-theoretic variance-reduction bound vs loop bandwidth & sensor noise | Symbolic/numeric bound asserts achievable variance given (A7) SNR and (A2) bandwidth. | Proof that closed-loop effective placement variance reaches target given measured loop bandwidth; else flag stiffening required. Jointly budget the averaging window N against the >=1000 motions/s rate floor (A2.4) and report the achievable (precision, rate) Pareto point, not precision alone: averaging N~100-400 to reach 1-2 nm caps rate at ~16-630/s unless cold-stiffening feedback or a 3-sigma noise read is invoked. | no |  | 2 | 4 | A1.1, A5.2, A7.1 |  |  | Feedback cooling limited by sensor SNR (A7).
A1.5 | Repeatability: return-to-target over >=100 actuation cycles | A | A1 | leaf | E | Closed-loop bench + FET/AFM readout | Acceptance test asserts 3-sigma return error <= spec across N cycles. | 3-sigma cycle-to-cycle repeatability <= target; no monotonic drift beyond tolerance. | YES | positional accuracy; TRL3->4 | 2 | 4 | A5.3 |  |  | Fatigue/creep of DNA/polymer.
A2.1 | Electromechanical model: stroke & blocking force vs gate voltage (HfO2-gated DNA lever) | A | A2 | leaf | P | Poisson-Boltzmann electrostatics + Euler-Bernoulli beam, closed form | Symbolic model + evaluator asserts stroke(V) and force(V) within breakdown-safe field. | Analytic stroke >=~3 nm (aspirational ~10 nm; acceptable if solidly repeatable or closed-loop-corrected) and blocking force >= 100 pN at gate field below HfO2 breakdown. Operating point: low-ionic-strength (spermidine Mg2+-free folding <1 mM, or ~2-3 mM Mg2+ with UV thymine-dimer/CPD covalent crosslinking) so the drive field is not screened away; spermidine-folded origami is documented stable under high field pulses. Note: lever length/stroke is NOT the dominant positioning-noise term -- JOINT COMPLIANCE is; budget stiffness at the joints and trade stroke vs amplification freely. | no |  | 3 | 4 |  |  |  | Debye screening at physiological ionic strength. | 32699450-4b41-474e-9f4e-cdbf9e3eee17
A2.2 | Field-driven deflection simulation incl. ionic screening | A | A2 | leaf | S | Poisson-Nernst-Planck + FEM | Sim harness asserts stroke & force vs voltage curve meets thresholds. | Simulated stroke >=~3 nm (aspirational ~10 nm), force >= 100 pN at <=2 V; screening length consistent with buffer. Evaluate stroke at the low-screening operating point (Mg2+-free / low-Mg + crosslink), not 10-20 mM Mg2+: the longer Debye length there preserves the work-stroke AND unscreens the FET sensor (A7). | no |  | 3 | 4 | A2.1 |  |  | Mesh/boundary sensitivity near electrode.
A2.3 | Fabricate gated electrode + tethered lever; measure voltage-displacement curve | A | A2 | leaf | E | HfO2 ALD gate + DNA-origami lever; FET / high-speed AFM readout | ASM acceptance test asserts reversible stroke & hysteresis vs spec from raw V-x data. | >=5 nm reversible stroke; hysteresis < 20%; reversible over >=10^3 cycles. | YES | force/displacement; TRL3->4 | 2 | 4 | A2.2 |  |  | THE key NDI feasibility gate: first molecular electrical actuator. | 4152dcb3-cbcd-486a-9aa0-3961a9529e60
A2.4 | Actuation bandwidth / cutoff frequency measurement | A | A2 | leaf | E | Small-signal frequency sweep + lock-in | Acceptance test asserts -3 dB bandwidth >= target. | Small-signal bandwidth >= 1 kHz (matches the prize floor of >=1000 positioning motions/s); roll-off characterized. | YES | SNR/speed; TRL3->4 | 2 | 4 | A2.3 |  |  | Viscous/drag limits at speed.
A2.5 | Dielectric reliability: field across HfO2 below breakdown over duty cycle | A | A2 | leaf | P | Field calc + Weibull TDDB model | Evaluator asserts operating field < breakdown with margin over device life. | Operating field <= 50% of HfO2 breakdown; projected MTTF > program duration. | no |  | 4 | 5 | A2.1 |  |  | Thin-film defects reduce real breakdown.
A2.6 | Backup-actuation trade study (electrochemical / electrowetting / dipole-field) | A | A2 | leaf | S | Comparative multiphysics trade model | Harness ranks candidates against stroke/force/speed/footprint thresholds. | >=1 backup mechanism meets A2 thresholds, de-risking single-point reliance on electrostatics. | no |  | 2 | 3 | A2.2 |  |  | Backups may need different chemistry/process.
A3.1 | Mobility / DOF proof for parallel (delta-type) molecular manipulator | A | A3 | leaf | P | Screw theory / Kutzbach criterion rank test | Rank/constraint checker asserts controllable DOF count. | >=3 independently controllable translational DOF; mechanism non-singular at home pose. | no |  | 3 | 4 |  |  |  | Compliant joints reduce effective DOF.
A3.2 | Workspace & singularity map within 100 nm envelope | A | A3 | leaf | S | Kinematic + compliant-mechanism FEM sweep | Harness asserts reachable workspace volume & singularity-free core region. | Reachable workspace covers the required 50 nm cube motion volume (per rules); singularity-free core >= X%; device envelope within 100 nm cube. | no |  | 3 | 4 | A3.1 |  |  | Thermal compliance shrinks usable workspace.
A3.3 | cryo-EM confirmation that as-assembled geometry matches design | A | A3 | leaf | E | cryo-EM single-particle reconstruction | ASM acceptance test asserts geometry deviation <= tolerance. | Assembled geometry within tolerance of CAD; correct topology in >= threshold of particles. | YES | geometry/assembly; TRL3->4 | 3 | 4 | A3.2, C2.2 |  |  | Mis-assembly / heterogeneity. | 68e0bb37-c8b0-4cd7-b290-5ed08f2634ca, e3c6b041-4899-56cd-9fc9-93deae35d1be
A4.1 | Tooltip grab/release energetics for a defined cargo | A | A4 | leaf | S | DFT / enhanced-sampling MD free-energy | Harness asserts deltaG window enabling controlled grab AND release. | Binding deltaG strong enough to hold under thermal load yet releasable by commanded actuation; window quantified. | no |  | 2 | 4 |  |  |  | Release may require force exceeding actuator (couples to A2).
A4.2 | Demonstrate controlled pick-and-place of a nanoscale object | A | A4 | leaf | E | Closed-loop manipulation + cryo-EM/AFM verification | Acceptance test asserts object placed at commanded site within tolerance, success-rate >= threshold. | Deterministic placement at commanded site (tolerance per spec) with success rate >= threshold over >= N trials. | YES | positional accuracy; TRL3->4 | 1 | 4 | A4.1, A5.3 |  |  | Closest analogue to the prize's core demonstration; high integration risk.
A4.3 | Low-force tooltip bond-formation feasibility (Track-2 mechanosynthesis link) | A | A4 | leaf | S | DFT reaction-path with catalyst; retraction-force estimate | Harness asserts required retraction force <= actuator capability. | Candidate single-site/catalytic reaction with retraction force <= ~100 pN (vs 3-6 nN uncatalyzed); barrier feasible. | no |  | 2 | 3 | A2.1 | DIV-3 |  | Catalytic route abandons universal Ge->Si->C path (Track-2 complication).
A5.1 | Unique-addressability proof for M actuators via E electrodes (crosstalk bound) | A | A5 | leaf | P | Crossbar/multiplex addressing proof + capacitive crosstalk bound | Symbolic/numeric checker asserts unique addressing and crosstalk < noise margin. | Each actuator uniquely addressable; worst-case crosstalk < sensing/actuation noise margin. | no |  | 3 | 4 |  |  |  | Wiring scales poorly with M (couples to E4).
A5.2 | Closed-loop control simulation (plant = A2 actuator + A7 sensor) | A | A5 | leaf | S | Control simulation (state-space / MPC) | Harness asserts settling time, steady-state error, and stability margins. | Steady-state error <= target, gain/phase margins adequate, stable under modeled noise. | no |  | 2 | 4 | A2.2, A7.2 |  |  | Plant model fidelity.
A5.3 | Closed-loop demonstration on a single actuator (command->move->sense->correct) | A | A5 | leaf | E | Integrated actuator + FET sensor + controller | Acceptance test asserts closed-loop sigma < open-loop sigma by required factor. | Closed-loop positional sigma reduced >= 2x vs open loop; the 'critical missing element' demonstrated. | YES | positional accuracy; TRL3->4 | 1 | 4 | A2.3, A7.3, A5.2 |  |  | Loop latency vs actuator bandwidth. | 0b80c825-6a28-41ad-a895-036c6fc7e227
A5.4 | AI control-model identification & held-out validation | A | A5 | leaf | S | System ID / ML surrogate trained on sensor feedback | ML eval harness asserts prediction error <= tolerance on held-out actuation data. | Model predicts displacement within tolerance on held-out set; generalizes across devices. | no |  | 2 | 4 | A5.3 |  |  | Distribution shift device-to-device.
A6.1 | Per-actuator power & local-heating budget | A | A6 | leaf | P | Joule/dielectric loss + heat-diffusion closed form | Evaluator asserts steady-state deltaT < limit. | Local temperature rise < limit at operating duty; aggregate array heat tractable. | no |  | 3 | 4 |  |  |  | Array-level heating in dense layouts.
A6.2 | Electrode electrochemical/electromigration stability at operating bias | A | A6 | leaf | S | Electrochemical-window + electromigration model | Harness asserts bias within stability window; no faradaic degradation. | Operating bias within electrochemical window; projected electrode life > program. | no |  | 3 | 4 | A2.5 |  |  | Buffer electrolysis at higher voltages.
A7.1 | Information-theoretic SNR bound for FET charge-displacement sensing vs bandwidth | A | A7 | leaf | P | Noise model (thermal/1-f/shot) + minimum detectable displacement derivation | Evaluator asserts min detectable displacement vs bandwidth B; flags feasibility of sub-3 nm @ target speed. | Closed-form min-detectable-displacement(B); explicit PASS/FAIL on sub-3 nm at >=1 kHz. The SNR bound MUST be computed at the actuator's operating ionic strength: in 10-20 mM Mg2+, screening attenuates the sensed charge ~10-50x; the low-Mg / Mg2+-free + crosslink operating point is required to reach SNR>=10 at >=1 kHz. | no |  | 3 | 4 |  |  |  | Directly addresses NDI's stated open risk. | 5ce20c61-7b33-4b26-bab8-2ab322ed0d81
A7.2 | Device simulation of FET sensitivity to lever charge vs distance/screening | A | A7 | leaf | S | TCAD / NEGF device sim | Harness asserts transconductance-derived SNR >= target. | Simulated SNR >= 10 at sigma=3 nm and B >= 1 kHz. Simulate at the low-ionic-strength operating point; report Debye length and sensed-charge attenuation vs Mg2+ (and spermidine) concentration. | no |  | 3 | 4 | A7.1 |  |  | Debye screening kills sensitivity at high ionic strength.
A7.3 | Measure FET displacement-sensing SNR vs speed | A | A7 | leaf | E | Fabricated FET adjacent to charged lever; lock-in | ASM acceptance test asserts measured SNR vs bandwidth meets A7.1 bound. | Measured SNR meets derived bound at operating bandwidth; sub-3 nm resolved at >=1 kHz. | YES | SNR; TRL3->4 | 2 | 4 | A7.2 |  |  | Parasitics/1-f noise in real devices.
A8.1 | Envelope proof: assembled arm bounding box <= 100 nm | A | A8 | leaf | P | CAD bounding-box / geometry checker | Geometry checker asserts max extent <= 100 nm in all axes. | Assembled manipulator fits <=100 nm cube; off-board control electrodes & anchoring substrate are EXCLUDED from the envelope (rules interpretation confirmed). | no |  | 3 | 4 | A3.2 |  |  | Functional structure (minus excluded electrodes/anchor) must still close the 100 nm envelope.
A8.2 | Structural rigidity / mechanical mode analysis | A | A8 | leaf | S | Normal-mode / FEM modal analysis | Harness asserts no soft mode degrades A1 positioning below spec. | Lowest relevant mode stiffness consistent with A1 stiffness bound; no floppy modes in workspace. Identify the dominant compliance term (joint compliance, not lever length) and budget stiffness at the joints. | no |  | 3 | 4 | A1.1 |  |  | Compliance (stroke) vs rigidity (precision) tension; key to whether prize-grade arm is reachable.
A8.3 | Operating-environment demonstration (declared medium/temperature) | A | A8 | leaf | E | Operation in declared environment (buffer/vacuum/cryo) | Acceptance test asserts function within declared environment per theory of operation. | Device operates to spec in the declared, prize-admissible environment; environment documented. | YES | operation; TRL3->4 | 2 | 4 | A5.3 |  | TBR-1 | Environment admissibility per rules (TBR-1).
A.INT | Integrated arm demonstration at prize spec (Gen-3+ prize-closing gate) | A | A | leaf | E | Closed-loop manipulation + cryo-EM/AFM/interferometric position tracking | Acceptance test asserts directed motion sequence within a 50 nm cube at <=0.1 nm accuracy, >=1000 motions/s sustained >=60 s. | Arm executes a directed position sequence anywhere within a 50 nm cube at <=0.1 nm accuracy and >=1000 accurate motions/s for >=60 consecutive seconds (the literal Device-1 spec). | YES | positional accuracy + throughput + endurance; prize-closing | 1 | 4 | A4.2, A5.3, A1.3, A8.3 |  |  | Gen-3+: 0.1 nm at 1 kHz for 60 s vastly exceeds Gen-1 sub-3 nm; gated on stiffening (A8.2/A1.4).
B6.1 | Architecture trade study & feasibility down-select | B | B6 | leaf | P | Area/energy/temperature budget model across candidate primitives | Evaluator asserts >=1 architecture closes area+energy+temperature within 50 nm cube. | Down-select >=1 primitive (molecular QCA / donor-SET / molecular-switch crossbar / mechanical rod-logic) that is positionally assemblable AND topographically readable and closes budgets for ~37 XOR-gate-equivalent (94 basic) within 50 nm; DNA strand-displacement ruled out on size/speed. | no |  | 2 | 3 |  | DIV-1 |  | Reframed (DIV-1): the adder is a build-target for arm-class assembly; the primitive must read out as surface bumps.
B1.1 | Formal equivalence of adder netlist to reference 8-bit adder | B | B1 | leaf | P | SAT/SMT/BDD combinational equivalence check | Solver returns UNSAT on miter = formal proof of equivalence over all 2^16 inputs. | Equivalence PROVEN for all 8-bit input pairs (exhaustive/symbolic). | no |  | 4 | 5 | B6.1 |  |  | Pure logic; independent of physics.
B1.2 | Device-level simulation reproduces full truth table with noise margin | B | B1 | leaf | S | Architecture device-physics simulator (QCA engine / SET / SPICE-like) | Harness asserts all 256x256 sums correct AND state-separation > noise margin. | 100% correct sums in sim; logic-state separation > k.kBT margin at operating T. | no |  | 2 | 4 | B6.1, B2.1 |  |  | Sim fidelity of molecular device physics.
B2.1 | Single-primitive device-physics simulation (bistability & switching energy) | B | B2 | leaf | S | QM/device sim of one cell/gate | Harness asserts bistable, distinguishable states with switching energy margin. | Primitive bistable; switching energy > kBT.ln2 by required margin at operating T. Reliability floor: the switching-barrier target for correct logic is ~15-30 kBT (bit-error-rate over a full 8-bit add), NOT the kBT.ln2 erasure (Landauer) floor; state the operating temperature this implies (room-T vs cryogenic). | no |  | 2 | 4 | B6.1 |  |  | Operating temperature may be cryogenic (SET route).
B2.2 | Fabricate & characterize a single primitive (one gate/cell) | B | B2 | leaf | E | APM fabrication (STM H-depassivation donor / molecular switch) + transport | ASM acceptance test asserts switching with margin from measured transport data. | Single primitive demonstrates reproducible switching with margin; matches B2.1. | YES | TRL3->4 device | 2 | 4 | B2.1 |  |  | May require 4.5 K LT-STM/AFM process. | d5cf1040-4cf9-4e53-86d1-3344b38ae721, 5bd37d9e-d987-50d1-9376-2f0df1980944
B2.3 | Bit-error-rate vs energy/temperature bound (Landauer + noise) | B | B2 | leaf | P | Thermodynamic/Shannon error bound | Evaluator asserts BER <= target for reliable 8-bit addition. | BER per gate low enough that full 8-bit add succeeds with required probability. Use the ~15-30 kBT reliability barrier (not kBT.ln2) as the BER basis; if room-temperature margins are infeasible, declare cryogenic operation explicitly. | no |  | 3 | 4 | B2.1 |  |  | Thermal errors dominate at room T for some routes.
B3.1 | Area-closure place-and-route proof within 50 nm cube | B | B3 | leaf | P | Packing/place-and-route checker at primitive pitch | Geometry checker asserts gates+wiring fit <=50 nm^3 with margin. | All ~37 XOR-equivalent (or 94 basic) gates + interconnect + bump-output transducers fit within 50 nm cube at chosen pitch. | no |  | 2 | 4 | B6.1, B1.1 |  |  | Wiring/interconnect dominates area (favors wireless QCA).
B3.2 | Crosstalk / coupling simulation between adjacent devices | B | B3 | leaf | S | Electrostatic/quantum coupling sim | Harness asserts inter-device coupling < logic noise margin. | Worst-case neighbor coupling < state-separation margin from B2.1. | no |  | 2 | 4 | B3.1 |  |  | Dense packing increases coupling.
B4.1 | I/O scheme proof (16-bit input via allowed modality; 8-bit output as surface bumps) | B | B4 | leaf | P | I/O modality + output-transduction proof | Checker asserts 16-bit input via an allowed modality and 8-bit topographic (bump) output are resolvable within the rules. | Input via an allowed modality (acoustic/electrical/optical/diffusive-chemical/mechanical-single-axis); 8-bit output (overflow discarded) rendered as raised nm-scale bumps on an atomically precise level surface, SPM-readable. | no |  | 2 | 4 | B3.1 |  |  | Bump-transduction (compute state -> surface topography) is itself a design problem.
B4.2 | Demonstrate 1-bit full-adder slice (input set + output read) | B | B4 | leaf | E | Fabricated full-adder cell + I/O | Acceptance test asserts correct sum+carry for all 8 input combinations. | 1-bit full adder renders correct sum & carry-out as surface bumps for all 8 input combinations; building block validated. | YES | TRL3->4 device | 1 | 4 | B2.2, B4.1 |  |  | Integration of I/O + bump transduction with the cell.
B5.1 | Energy/heat per addition & integrity budget | B | B5 | leaf | P | Energy-per-op + heat-diffusion model | Evaluator asserts deltaT < limit at required throughput. | Energy/op and heat within limits for the declared throughput. | no |  | 3 | 4 | B2.3 |  |  | Cooling of a 50 nm hotspot.
B.INT | Integrated 8-bit adder demo (<=50 nm; exhaustive 65,536 inputs; bump output) | B | B | leaf | E | Full device + SPM topographic readout | Acceptance test asserts correct 8-bit sum (overflow discarded) for ALL 65,536 input pairs, read as surface bumps; envelope <=50 nm verified. | Adder returns correct 8-bit sum (overflow discarded) for all 65,536 (2^16) input pairs, output as raised nm-scale bumps on an atomically precise level surface; device <=50 nm; produced by arm-class positional assembly. | YES | prize-closing demonstration; exhaustive; TRL3->4 | 1 | 4 | B1.2, B3.2, B4.2, B5.1, A.INT, A4.3 | DIV-1 |  | Prize-closing gate for Device 2; depends on Gen-3+ arm/mechanosynthesis capability to build it.
C1.1 | Yield-budget proof: max tolerable per-step defect rate for >=32 good devices | C | C1 | leaf | P | Yield model y^N + Monte-Carlo | Evaluator asserts required per-step yield for 32 devices at confidence c; flags infeasible routes. | Per-step yield target derived for N steps to deliver 32 devices at confidence c (e.g., 99%); architecture flagged if infeasible. | no |  | 3 | 4 |  |  |  | Serial SPM N huge -> favors self-assembly + selection.
C2.1 | Hierarchical self-assembly yield simulation (staged folding/binding) | C | C2 | leaf | S | Kinetic/thermodynamic assembly sim | Harness asserts predicted correctly-formed fraction >= threshold. | Predicted correctly-assembled fraction >= threshold consistent with C1 budget. | no |  | 2 | 4 | C1.1 |  |  | Hierarchical assembly unproven in this on-chip context.
C2.2 | Measure bulk assembly yield (gel / AFM / cryo-EM particle classification) | C | C2 | leaf | E | Bulk characterization + cryo-EM classification | ASM acceptance test asserts correctly-formed fraction >= threshold. | Measured correctly-formed fraction >= threshold; defect modes catalogued. | YES | yield; TRL3->4 | 3 | 4 | C2.1 |  |  | Low yield -> heavier reliance on C3. | 1405b2bd-1b28-4b91-93e8-70884158f84a
C3.1 | Selection/purification to obtain 32 spec-conforming devices | C | C3 | leaf | E | Affinity/size selection + per-device screen | Acceptance test asserts 32 devices each pass A & B acceptance. | 32 devices isolated, each independently passing SEG-A (and SEG-B) acceptance AND able to survive destructive testing by judges (no hero-device reuse). | YES | yield; prize-closing | 2 | 5 | C2.2, A4.2 |  |  | Per-device screening throughput.
C4.1 | Device-to-device reproducibility distribution across 32 copies | C | C4 | leaf | E | Batch metrology of key metrics | Acceptance test asserts all 32 within spec band (+/- tolerance on stroke, SNR, accuracy). | All 32 devices within spec band on key metrics; distribution reported. | YES | yield/accuracy; prize-closing | 2 | 5 | C3.1 |  |  | Tail devices fail spec.
C5.1 | [Roadmap link] Self-replication / exponential scale-up beyond x32 (Gen-3) | C | C3 | leaf | P | Closure/replication-fraction analysis | Evaluator asserts replication fraction & closure assumptions; out-of-prize-scope marker. | Documented as NDI Gen-3 path (hierarchical convergent assembly); OUT of prize scope (rules: self-replication NOT required) but in roadmap. | no |  | 1 | 2 | C4.1 |  |  | Bootstrapping/closure unsolved; long horizon. | 7ab290df-9be7-442b-9254-beac38b625d7
D1.1 | Metrology adequacy proof: tool resolution < required tolerance per measured quantity | D | D1 | leaf | P | Resolution-vs-tolerance comparison | Evaluator asserts each tool's resolution < spec tolerance; flags gaps. | Each measured quantity assigned a tool whose resolution beats its tolerance (cryo-EM ~few A; smFRET 2-8 nm; AFM 3-8 nm gap); 0.1 nm prize accuracy flagged as a metrology challenge. | no |  | 5 | 6 |  |  |  | 0.1 nm verification at >=1 kHz may exceed current metrology; flag gap. | 7d76c62c-8be0-4e08-8145-7d76127ccf16
D2.1 | Screening design: power analysis for bulk ensemble vibration screen | D | D2 | leaf | S | Statistical power analysis | Harness asserts sample size resolves target effect at required power. | Bulk screen sized to detect target stiffness/displacement effect at >=80% power; throughput estimated. | no |  | 4 | 5 |  |  |  | Ensemble averaging hides per-device tails.
D2.2 | Single-molecule AFM force/displacement on down-selected designs | D | D2 | leaf | E | Single-molecule force spectroscopy (AFM) | ASM acceptance test asserts measured force/displacement matches sim within tolerance. | Best designs' force/displacement match simulation within tolerance; precise characterization recorded. | YES | force/displacement; TRL3->4 | 3 | 5 | D2.1 |  |  | Tip/coupling artifacts.
D3.1 | Automated acceptance-test harness: instrument output -> ASM JSON -> assertion | D | D3 | leaf | S | Allotrope ASM converter + assertion engine (instrument-data-to-allotrope) | Harness deterministically PASS/FAIL a node from raw instrument data; versioned spec thresholds. | Given raw instrument file + node spec, harness emits reproducible PASS/FAIL; makes empirical leaves machine-verifiable. | no |  | 4 | 6 |  |  |  | Schema coverage across instruments.
D4.1 | Theory-of-operation completeness & independent-rebuild check | D | D4 | leaf | E | Documentation audit + independent reconstruction | Acceptance test asserts an independent team rebuilds a device from the package and passes acceptance. | Submission package complete per Foresight rules; independent rebuild reproduces a passing device. | YES | reproducibility; prize submission | 2 | 5 | A4.2, B.INT |  | TBR-1 | Tacit knowledge not captured.
E1.1 | Fabricate e-beam-patterned electrode array at required pitch & registration | E | E1 | leaf | E | EBL + metrology of pitch/registration | ASM acceptance test asserts pitch & registration <= tolerance. | Electrode array at required pitch with registration <= tolerance (EBL ~75 nm feature floor; sub-feature alignment strategy documented). | YES | registration accuracy; TRL3->4 | 4 | 5 |  |  |  | EBL feature floor vs molecular pitch mismatch. | 7d76c62c-8be0-4e08-8145-7d76127ccf16
E2.1 | Anchoring design: site-specific attachment occupancy & orientation model | E | E2 | leaf | S | Binding/orientation model (dual-anchor SpyCatcher/SnoopTag analogue) | Harness asserts predicted correct-orientation occupancy >= threshold. | Predicted correct-orientation occupancy >= threshold; mis-orientation modes enumerated. | no |  | 3 | 4 |  |  |  | Non-specific binding / orientation scatter.
E2.2 | Measure anchoring yield & orientation (cryo-EM / FRET) | E | E2 | leaf | E | cryo-EM / smFRET orientation assay | ASM acceptance test asserts measured occupancy & orientation >= threshold. | Measured correct-orientation occupancy >= threshold; consistent with E2.1. | YES | yield/orientation; TRL3->4 | 3 | 4 | E2.1 |  |  | Interface heterogeneity.
E3.1 | Real-time control-loop latency & stability budget | E | E3 | leaf | P | Loop-delay/stability budget (sensor BW + compute + actuator BW) | Evaluator asserts loop phase margin adequate at target bandwidth. | End-to-end loop latency yields adequate phase margin at target control bandwidth. | no |  | 3 | 4 | A2.4, A7.1 | DIV-2 |  | Off-board round-trip latency.
E3.2 | AI control model: train on sensor feedback, validate on held-out | E | E3 | leaf | S | ML control surrogate + eval | ML eval harness asserts displacement-prediction error <= tolerance on held-out. | Model meets held-out error tolerance; supports closed-loop in A5. | no |  | 2 | 4 | A5.4 |  |  | Data efficiency / sim-to-real gap.
E4.1 | Array-addressing scalability proof (wiring vs N actuators) | E | E4 | leaf | P | Multiplex/wiring scaling proof | Evaluator asserts addressable N within electrode/wiring budget & crosstalk bound. | Addressing scheme scales to target array size within wiring & crosstalk budget. | no |  | 2 | 4 | A5.1 |  |  | Wiring is the practical ceiling on array size. | aa09dec9-d2a8-4494-9bd0-a10c665718d2
I1.1 | Silicified / covalently-crosslinked bio structure | I | I1 | leaf | E | Silica coating and/or UV/covalent crosslinking of DNA/protein | Acceptance test asserts the stabilized structure retains geometry and stiffness through dehydration/vacuum and a salt-free rinse. | Make the Gen-2 bio structure survive dehydration/vacuum without denaturing: SILICIFICATION penetrates DNA origami and raises Young's modulus ~10x (100 MPa -> 1 GPa), stable without salt buffers and at elevated temperature; and/or COVALENT crosslinking (UV/thymidine, oligolysine) stabilizes origami to ~90 C and in pure salt-free water. The stabilized structure also survives the [application obligation] salt-free clean. | YES | vacuum/dehydration survival | 2 | 3 |  |  |  | Silica/crosslink may embrittle hinges or fix joints in the wrong pose.
I1.2 | Fully-inorganic NEMS templated / cast by bio-NEMS | I | I1 | leaf | E | DNA-mold casting / DNA-programmable inorganic templating | Acceptance test asserts a cast/templated inorganic mechanical element with functional, correctly-bound joints. | Use Gen-2 bio-NEMS (in fluid) to template/CAST a fully-inorganic NEMS mechanism: DNA molds cast metal/semiconductor parts to sub-5 nm replicating the mold; 3D metal/oxide/semiconductor frameworks via DNA-programmable templating are demonstrated. The crux is JOINT/HINGE fidelity - the assembled inorganic mechanism's joints must be bound/constrained correctly. Extend to protein-assembler positioning: ~2-3 nm engineered-protein nanomachines (crosslinked joints) place pre-fabricated stiff inorganic members (CNTs, piezoelectric nanowires) into the target mechanism; joint/hinge fidelity is the crux until inorganic joints become mechanosynthesizable. (Joint material is an open design variable; leading candidate is engineered proteins used as the linkages between inorganic members.) | YES | inorganic mechanism by bio template | 1 | 3 | I1.1 |  |  | Joint/hinge fidelity is the make-or-break (Barton).
I2.1 | Vacuum-native actuator layer (non-DNA) | I | I2 | leaf | E | Electrostatic comb/gap, piezo, or electrothermal actuation | Acceptance test asserts the actuator delivers spec force/stroke/bandwidth in vacuum at the manipulator scale. | Replace DNA-electrostatic actuation (needs water/ions) with a vacuum-native actuator - electrostatic comb/gap drive, piezo, or electrothermal - delivering the required force/stroke/bandwidth at the manipulator scale in vacuum (the standard regime for NEMS actuators/resonators). | YES | actuation in vacuum | 2 | 3 |  |  |  | Force density and integration with the stabilized structure.
I3.1 | Fluid -> vacuum environmental transition interface | I | I3 | leaf | S | Stabilize -> rinse -> critical-point/freeze dry -> pump-down sequence | Harness asserts a transition sequence the structure survives, with the schedule/interface impact documented. | Define the explicit fluid->vacuum transition (stabilize -> salt-free rinse -> critical-point/freeze dry -> pump-down) that the stabilized structure survives, and capture its impact on the program sequence (likely DELAYS CMOS integration) as a controlled systems-engineering interface. | no |  | 1 | 3 | I1.1, I2.1 |  |  | Each transition step risks structure loss; adds schedule (Barton).
I3.2 | Vacuum payoff proof (relaxes the fluid obligations) | I | I3 | leaf | P | Map vacuum regime onto the the application track fluid obligations | Evaluator asserts each fluid-regime obligation ([application obligation]/[application obligation]/[application obligation]) is relaxed or retired under vacuum operation. | Quantify the vacuum payoff: in-line electrical gate-sweep test is valid (no ~1 nm Debye screening), there is no aqueous mobile-ion source, dry vdW returns to full strength (16-48 pN peel / 1e2-1e3 kBT pin), and there is no capillary dry-down - so vacuum operation relaxes/retires [application obligation] (wet pin), [application obligation] (mobile-ion barrier-vs-probe) and [application obligation] (staged wet/dry loop), and the Round-5 in-fluid live-device block. | no |  | 2 | 3 | I3.1 |  |  | Outgassing / vacuum adsorbates; tube and contact stability in vacuum.
I3.3 | Bootstrap: Gen-2 builds the Gen-3 vacuum substrate | I | I3 | leaf | E | Gen-2 fluid bio-NEMS fabricating an inorganic Gen-3 substrate | Acceptance test asserts a Gen-3 vacuum-operating substrate fabricated by Gen-2 fluid manipulators from CMOS-like materials. | Demonstrate the generational handoff: Gen-2 fluid bio-NEMS manufacture the Gen-3 vacuum-operating substrate out of CMOS-like materials (Si/SiO2/SiN), validating that the fluid generation bootstraps the vacuum generation. | YES | generational bootstrap | 1 | 3 | I3.1 |  |  | Throughput/fidelity of bio-NEMS building an inorganic substrate.
J1.1 | Gen-1 actuator + lever + thermal-noise model | J | J1 | leaf | S | Coarse-grained/MD origami stiffness + electrostatic voltage-controlled-spring + thermal spectrum | Harness asserts the modeled force-displacement and closed-loop position spectrum meet the 100 nm/20 pN and 1-2 nm-in-20 nm targets. | Model the Gen-1 stack (patterned electrode / high-k dielectric / soft polymer / DNA-origami Class-3 lever) as a voltage-controlled spring: predict force-displacement (target 100 nm displacement, 20 pN at the load), the Class-3 amplification, and the thermal-noise spectrum (~+-20 nm raw) -> the closed-loop precision achievable (1-2 nm in a 20 nm volume). | no |  | 3 | 4 |  |  |  | Hinge stiffness and polymer restoring force set the achievable precision.
J1.2 | Gen-1 closed-loop actuator demonstration (the true first bench gate) | J | J1 | leaf | E | Fold + TEM/AFM validate; electrostatic actuation; FET closed-loop | Acceptance test asserts a folded lever actuates to spec, the adjacent FET senses position, the loop closes, and 1-2 nm precision is reached in a 20 nm volume. | Fold the DNA-origami Class-3 lever and validate by TEM/AFM; electrostatically actuate (100 nm displacement / 20 pN at load); sense position with an adjacent MOSFET (charged DNA backbone modulating the gate); CLOSE THE LOOP (the critical missing element of Iteration 1); achieve 1-2 nm precision in a 20 nm volume despite ~+-20 nm raw thermal noise. This is the foundational gate the entire program presupposes. Stroke figures reconciled: ~100 nm is the Class-3 lever-amplified COARSE displacement; ~5-10 nm is the fine working stroke; ~20 nm is the closed-loop working volume. Operate at the low-ionic-strength point (spermidine / low-Mg + CPD crosslink). | YES | foundational closed-loop demo; gates everything | 2 | 4 | J1.1, D1.1 |  |  | Closed-loop sensing SNR (FET) and fold yield (Kopperger Science 2018 is the electric-field precedent).
J1.3 | Gen-1 addressable actuator array | J | J1 | leaf | E | Voltage-routed patterned-electrode addressing | Acceptance test asserts independent per-actuator control across a multi-actuator array via voltage routing. | Demonstrate a multi-actuator array with individual addressing by voltage routing to patterned electrodes (display/memory-pixel-like; no mechanical selectivity), with independent per-actuator closed-loop control - the bridge to the the scaled manipulator array. | YES | array addressing demo | 2 | 4 | J1.2, E4.1 |  |  | Crosstalk and per-site sensing at array density.
J2.1 | Gen-2 protein-stiffened / functional NEMS model | J | J2 | leaf | S | De-novo protein design (RFdiffusion/ProteinMPNN) + stiffness/thermal model on origami scaffold | Harness asserts the protein-augmented structure model reaches +-2-5 nm with the targeted functional element positioned to tolerance. | Model protein-augmented NEMS: de-novo proteins (RFdiffusion/ProteinMPNN, Baker-lab class) docked at origami handles (~200 addressable points/tile) predicted to reduce thermal noise to +-2-5 nm and add stiffness/durability, with a functional element (motor / switch / enzymatic active site) positioned to ~Angstrom. | no |  | 2 | 3 | J1.1 |  |  | De-novo protein design fidelity and protein-DNA interface stability.
J2.2 | Gen-2 protein-augmented NEMS demonstration | J | J2 | leaf | E | Protein-on-origami assembly + characterization on the Gen-1 bus | Acceptance test asserts a protein-augmented device reaches +-2-5 nm and positions a functional element to tolerance, driven by the Gen-1 electrostatic+FET bus. | Demonstrate de-novo proteins docked at origami handles reaching +-2-5 nm thermal noise with improved stiffness/durability and a functional element (motor/switch/enzymatic active site) positioned to ~Angstrom, actuated and sensed on the Gen-1 electrostatic+FET bus. | YES | protein-augmented platform demo | 1 | 3 | J2.1, J1.2 |  |  | Protein-DNA hybrid durability in the operating environment.
J3.1 | Gen-3 stiffening-gap proof (toward sub-nm) | J | J3 | leaf | P | Stiffness-wall calculation: required vs achievable torsional stiffness | Evaluator asserts the proposed stiffening design (protein and/or inorganic SEG-I) closes the torsional-stiffness gap to k ~ 0.41 N/m for sub-nm placement, AND confirms this is prize-track only (not required for the downstream placement application, which uses kinematic-stop registration). | Prove the stiffening design closes the gap between measured DNA-origami hinge/torsional stiffness (far too low) and k ~ 0.41 N/m required for sub-nm (0.1 nm) placement (vs only ~0.46 pN/nm for 3 nm) - the gating physics for the prize-grade arm (SEG-A) ONLY. Dense-pitch placement does NOT require this: the commercial midpoint hits its tolerance via kinematic-stop registration (~1-3 nm), not sub-nm stiffness. The route that closes the gap is likely INORGANIC (vacuum/inorganic branch, SEG-I), not protein stiffening alone. Quantify required-vs-achievable and the design (protein and/or inorganic) that closes it. Route update: pursue sub-nm NOT by stiffening a protein arm to k~0.41 N/m, but by using ~2-3 nm protein-component assemblers (crosslinked, engineered protein joints) to POSITION stiff inorganic members (CNTs, piezoelectric nanowires); protein joints persist until mechanosynthesis-competent inorganic joints exist. Quantify required-vs-achievable for the assembler+inorganic-member stiffness, not the bare protein. (Joint material is an open design variable; leading candidate is engineered proteins used as the linkages between inorganic members.) | no |  | 2 | 3 | J2.1 |  |  | The stiffness wall may not be reachable with protein stiffening alone (then inorganic/SEG-I is required).
J3.2 | Gen-3 sub-nm closed-loop placement demonstration | J | J3 | leaf | E | Stiffened structure + closed-loop placement | Acceptance test asserts sub-nm closed-loop placement by the stiffened structure. | Demonstrate sub-nm closed-loop placement with the protein-stiffened structure - the precursor tier to the Gen-3+ Feynman-prize-grade arm (SEG-A) and the enabler of dense-pitch placement precision. | YES | sub-nm gate; precursor to prize-grade | 1 | 3 | J3.1 |  |  | Sub-nm under thermal noise even with stiffening; may require Gen-3 vacuum (SEG-I).
AG.1 | Accuracy gate: 0.1 nm | A | AG | leaf | P | Required-vs-achievable accuracy ledger | Evaluator asserts the demonstrated arm positioning accuracy is recorded against the 0.1 nm requirement and flags the gap until met. | REQUIRED 0.1 nm. ACHIEVABLE: Gen-1 1-2 nm, Gen-2 +-2-5 nm, Gen-3 sub-nm (gated). DELTA ~10-20x. CLOSES at Gen-3+ only, contingent on J3.1 closing the torsional-stiffness wall to k~0.41 N/m (vs ~0.46 pN/nm at 3 nm). NOT met in Phases 0-1. | no |  | 2 | 4 | J3.1 |  |  | Stiffness wall may be unreachable with protein stiffening (then SEG-I vacuum/inorganic).
AG.2 | Force gate: ~100 pN to ~nN | A | AG | leaf | P | Required-vs-achievable force-floor ledger | Evaluator asserts delivered load force is recorded against the mechanosynthesis force floor. | REQUIRED mechanosynthesis force floor ~100 pN (single-site-catalysis target) to ~nN (Ge-C bond breaking). ACHIEVABLE: Gen-1 ~20 pN at load. DELTA ~5-100x. CLOSES at Gen-2/3 stiffening + the single-site-catalysis force relaxation. NOT met at Gen-1. | no |  | 2 | 4 | J3.2 |  |  | Stiffer structure must still deliver force without losing precision.
AG.3 | Rate gate: >=1000 motions/s for >=60 s | A | AG | leaf | S | Bandwidth-vs-noise model (cadence vs averaging) | Harness asserts the modeled sustained motion rate at the required accuracy meets >=1000/s for >=60 s. | REQUIRED >=1000 motions/s sustained >=60 s (>=6e4 motions). ACHIEVABLE: closed-loop verify/settle cadence ~tens of ms (~16/s in the downstream placement application) -> ~60x short, and in direct tension with averaging-down to 0.1 nm. Quantify via the J1.1 bandwidth-vs-thermal-noise model; CLOSES at Gen-3+. | no |  | 1 | 3 | J1.1 |  |  | Rate and 0.1 nm accuracy trade off through the averaging time.
AG.4 | Atomically-precise-output gate (the defining deliverable) | A | AG | leaf | P | Output-precision class ledger (nanomaterial vs atomic) | Evaluator asserts the output precision class is recorded against the atomically-precise requirement. | REQUIRED: arm = positional mechanosynthesis engine outputting an ATOMICALLY-PRECISE object; the 8-bit adder is built on an atomically-precise surface. ACHIEVABLE: Gen-1/2/3 place NANOMATERIALS at 1 nm-to-sub-nm, NOT atoms - a categorical gap. CLOSES at Gen-4+ (cryo-STM mechanosynthesis). The defining prize deliverable is two tiers beyond the bio-platform. | no |  | 1 | 4 |  |  |  | Atomically-precise positional assembly is a different capability class than nanomaterial placement.
AG.5 | Size gate: <=100 nm arm / <=50 nm adder | A | AG | leaf | S | Dimensional ledger vs device count | Evaluator asserts arm cube/workspace and adder cube are recorded against the size limits and the device-density implication flagged. | REQUIRED arm <=100 nm cube, 50 nm workspace; adder <=50 nm cube. ACHIEVABLE: arm ~IN RANGE at Gen-1/2 (~20 nm volume, lever extendable; off-board control excluded per DIV-2) - the one axis ~met. But a <=50 nm 8-bit adder (~hundreds of devices) demands atomic-density logic -> BINDING, closes at Gen-4+. | no |  | 2 | 4 |  |  |  | The adder size, not the arm size, is the binding dimensional constraint.
AG.6 | Prize-readiness rollup & go/no-go | A | AG | leaf | S | Conjunction of AG.1-AG.5 + the stiffness-wall decision | Harness asserts prize-ready = AG.1 AND AG.2 AND AG.3 AND AG.4 AND AG.5 all pass; otherwise reports the binding axes and generation. | PRIZE-READY only when AG.1-AG.5 all pass: arm axes (accuracy/force/rate) at Gen-3+ AND atomically-precise output + <=50 nm adder at Gen-4+. Near-term Phases 0-1 (Gen-1/2) do NOT meet it. GO/NO-GO: if J3.1 cannot close the stiffness wall with protein stiffening, the prize-grade arm requires the Gen-3 vacuum/inorganic route (SEG-I). NOTE the revision relaxed FORCE (single-site catalysis) and the ADDER output-form (any readable output, <=100 kT/bit-op) but NOT the 0.1 nm accuracy or the <=50 nm adder size. | no |  | 2 | 4 | AG.1, AG.2, AG.3, AG.4, AG.5 |  |  | The binding gaps (0.1 nm accuracy; atomically-precise <=50 nm adder) are unrelaxed by the output-defined restatement.
A7.4 | Coupled actuation-stroke + FET-sense SNR vs ionic strength (operating-window proof) | A | A7 | leaf | S | Coupled Poisson-Boltzmann + FET electrostatics vs ionic strength | Evaluator confirms a single ionic-strength window meets BOTH stroke>=10 nm/force>=100 pN and FET SNR>=10 at >=1 kHz. | Solve the coupled Poisson-Boltzmann problem for the gated lever + adjacent FET as ONE system vs ionic strength: show an operating window (candidate: spermidine Mg2+-free folding <1 mM, or ~2-3 mM Mg2+ with UV/CPD covalent crosslinking) that SIMULTANEOUSLY delivers actuator stroke >=~3 nm (aspirational ~10 nm; repeatable or closed-loop-correctable) / force >=100 pN AND FET charge-sensing SNR >=10 at >=1 kHz. Report Debye length, work-stroke, and sensed-charge attenuation across the Mg2+/spermidine range. This jointly resolves the actuator(needs ions)-vs-sensor(needs low screening) conflict raised in review. | no |  | 1 | 3 | A2.1, A7.1 |  |  | Actuator (needs ions) and FET sensor (needs low screening) conflict; low-Mg/Mg2+-free + CPD crosslink is the proposed joint solution but unproven.